Production Timeline for 2021 University Bulletin

| November 2020 | - Initial Bulletin meeting to discuss production for 2021 |
| --- | --- |
| January 2021 | - Update list of content owners and editors and OU permissions - Liz updates list in Excel spreadsheet and sends to Gerald - Gerald/Patrick update list of users and permission levels in OU - Set up files in OU for 2021 Bulletin cycle - Need to decide who will do this – Gerald/Patrick or Helen/Craig? - Liz meets with Grad School to discuss process for 2021 - Liz meets with Harpur College to discuss process for 2021 |
| SPRING SEMESTER CLASSES BEGIN 2/8 (Grad Nursing and Pharm) and 2/11 (all others) |  |
| Feb 15-March 19 (5 weeks) | - Editing by departments and offices |
| March 22- April 9 (3 weeks) | - Dean’s review period in OU |
| April 12-May 7 (4 weeks) | Grad School reviews: - Policy sections - 3/2 and graduate sections: Grad School reviews and alerts Liz and Lori when they are complete |
| April 12-May 7 (4 weeks) | Liz does Provost’s Office review, including all front sections, all policy sections, and all UG sections and will alert Lori when review of each section is complete. |
| April 12-May 21 (6 weeks) | Lori begins proofreading sections as they are cleared by Liz and/or the Graduate School; all major changes should be made by May 21 |
| May 1 | Bulletin Faculty database done and submitted by Lynne Hendee |
| CLASSES END 5/18; FINALS 5/19-21 AND 5/24-26 |  |
| May 21 | All major changes made by COB so that Helen and Craig can upload content for next week’s review period – will need to publish the whole site. |
| May 24-June 4 (2 weeks) | Allow departments and offices to review their content on a temporary review site. |
| May 24-June 11 (3 weeks) | Make corrections and finalize Bulletin. Lori and Liz will publish changes as they are made. |
| June 14 | Bulletin goes live for Orientation (1st transfer Orientation is ???) |

Notes:

- As Bulletin edits are made, this may result in changes to the main page layout, menus or dropdowns. Liz will work with Helen/Craig on this.

- As updates to the Faculty list are made, this may result in changes to the Faculty pulldown lists.  Lynne Hendee will work with Helen/Craig on this.